## Sheet1
Start Week | End Week | Task | Total Duration (in Weeks)
1 | 6 | Research and learning | 5
2 | 5 | Project contract, ethical review, Global checklist | 3
5 | 8 | Literature review, test plan | 3
8 | 11 | system design, functional requirement | 3
10 | 11 | Diagrams | 1
11 | 25 | Coding | 15
11 | 12 | Database Setup | 2
13 | 16 | CRUD Operation + Inventy System | 3
15 | 19 | Login + Sign up for recommendations interface | 5
20 | 25 | Order placing interface | 6
11 | 25 | Testing | 15
26 | 31 | Final report, presentation, vivia | 5